## Stakeholder Matrix
Stakeholder Name | Job Title | Department | Project Role | Location | Communication Level of Detail | Influence of Stakeholder | Impact on Stakeholder | Project Expectations

## Stakeholder Analysis
Stakeholder Group | Stakeholder Name | Their Role in Change Effort | Stakeholders' Interests/attitudes/priorities/views on project | Influence on Program Success | Desired Level of Commitment | Current Level of Commitment | Gap in Commitment | Overview of Engagement Actions | Program Team Member Assigned | Due Date
End Customer | Nikki Gniadek | Nikki is a dissatisfied customer who recently purchased a squeaky dog toy and filed a complaint with the Argo's customer service team. | Nikki wants to continue purchasing dog toys but is concerned about the current level of quality. His priority is receiving a quality product, which he paid for. Nikki's view on the project is favorable since he wants to see products improve. | Medium | Aware | Aware | Low | N/A | Customer Service Manager | 2023-10-01
End Customer | Toto Gniadek | Toto is a dissatisfied customer who recently purchased a squeaky dog toy and filed a complaint with the Argo's customer service team. | Toto wants to continue purchasing dog toys but is concerned about the current level of quality. His priority is receiving a quality product, which he paid for. Toto's view on the project is favorable since he wants to see products improve. | Medium | Aware | Aware | Low | N/A | Customer Service Manager | 2023-10-01
End Customer | Steven Gniadek | Steven is a dissatisfied customer who recently purchased a squeaky dog toy and filed a complaint with the Argo's customer service team. | Steven wants to continue purchasing dog toys but is concerned about the current level of quality. His priority is receiving a quality product, which he paid for. Steven's view on the project is favorable since he wants to see products improve. | Medium | Aware | Aware | Low | N/A | Customer Service Manager | 2023-10-01
Former Customer | Becca Johnson | Becca WAS a dog toy customer, however, due to receiving multiple poor-quality squeaky dog toys, she has decided to take her business elsewhere. | This project is a low priority for Beccca, however, her views on the dog toy's company initiative to help improve products are favorable. Despite her dissatisfaction, she doesn't want other customers to suffer with the same frustrating experience she had. | Medium | Aware | Aware | Low | N/A | Customer Service Manager | 2023-10-01
Customer Service Manager | Diane Lane | Diane is the Customer Service Manager for the Argo. She leads the Customer Service team, and is very committed and interested in helping in this initiative as her staff is currently overwhelmed and frustrated with the seemingly neverending sea of customer complaints. | Diane's interests in this project are high. Her views are favorable. | High | Committed | Committed | Low | N/A | Project Owner | 2023-10-01 | GO HOME!!
Customer Service Team Member | Thomas Smith | Tom is a member of the customer service team at the Argo. Tom is frustrated and stressed day in and out due to the high volume of customer complaints he receives. | Tom's interests in this project are high. His views are favorable. | High | Committed | Committed | Low | N/A | Customer Service Manager | 2023-10-01
Customer Service Team Member | Emma Downey | Emma is a member of the customer service team at the Argo. Emma is not only frustrated with the high volume of customer complaints he receives, but she is angry that the company hasn't done anything about it yet. She is considering other job opportunities. | Emma's interests in this project are high. Her views are uncertain. | Medium | Buy-in | Aware | Medium | Diane will need to communicate with Emma that, emotions aside, Emma is a valued member of the team and her perspectives, opinions, and ideas are valuable to helping the improvement initiative become a success. | Customer Service Manager | 2023-10-01
Operations Manager | Annie Dewey | Annie is the Ops Manager for the Argo. Annie is losing sleep at night over the squeaky dog toy quality problem she is dealing with at work. She is stressed, frustrated, and quite frankly, worried about her job. She will do whatever is necessary to help improve things. | Annie's interests in this project are high. Her views are favorable. | High | Committed | Committed | Low | N/A | Project Owner | 2023-10-01
Cryer Supplier | John Hodgdon | John is the manager at Cryer, one of the Argo's main suppliers of the squeaky dog toy materials. John has heard "rumblings" about the Argo, Cryer's largest customer account, is dissatisfied, but no one from the Argo has approached him yet. If there's something he can do to work with his client to improve, he will. | John's interests in this project are high. His views are favorable. | High | Committed | Aware | High | The project owner will need to meet with John to describe the problem domain regarding the squeaky dog toy quality, ask him to be a part of the project team, and agree on his role and level of involvement. | Project Owner | 2023-10-01
Whiner Supplier | Beverly St. Andre | Beverly is the manager at Whiner, one of the Argo's main suppliers of the squeaky dog toy materials. Beverly knows the Argo is having issues, but it's not her problem. She is confident in the operations at her company. After all, the Argo is just ONE customer out of many. So, she thinks the Argo's customers are just being "whiny". | Beverly's interests in the project are low. Her views are unfavorable. | High | Aware | Unaware | Medium | The Ops manager will need to communicate with Beverly that her involvement and interests are key to the success of BOTH companies. | Operations Manager | 2023-10-01
Argo CEO | Ayesha Hooksett | Ayesha is Argo's CEO. Although she doesn't have a direct role in the project, she wants to see her company succeed, wants to avoid a poor reputation among customers, and is concerned about decreasing sales. | Ayesha's interests are high and her views are favorable. | Medium | Buy-in | Buy-in | Low | N/A | Project Owner | 2023-10-01
Project Owner | Jade Barrington | Jade is the project owner for the Argo rework project. She is the primary POC and decision-maker in the project and has a very active role. | Jade's interests are high and her views are favorable. | High | Committed | Committed | Low | N/A | CEO | 2023-10-01

## Stakeholder Map
Address Concerns | Enlist their help
Keep Informed | Involve as needed